## Sheet1
Stevo, Marco, Mehmo, Fernando - Android Platform using Java
Tasks | Description | Estimate | Task assigned to: | Task / Week | 2011-10-31 | 2011-11-07 | 2011-11-14 | 2011-11-21 | 2011-11-28 | 2011-12-05 | 2011-12-12 | 2011-12-19 | 2012-01-02 | 2012-01-09
1 | Loading Circle to Screen | 3 | Fernando | 1
1.1 | Get Circle to bounce on spot | 3 | Marco | 1.1
1.2 | Collision Detection with Platform (Leaf) | 4 | Marco | 1.2
2 | Accelerometer Implimented | 8 | Mehmet | 2
2.1 | Set Boundaries | 2 | Mehmet | 2.1
3 | Gamestate (Menu) | 2.5 | Stephen | 3
3.1 | Gamestate (Level #) | 2.5 | Stephen | 3.1
3.2 | Gamestate (Pause) | 2.5 | Stephen | 3.2
3.3 | Gamestate (Gameover) | 2.5 | Stephen | 3.3
4 | Parallex Scrolling | 4 |  | 4
5 | Timer Implimented | 2 |  | 5
6 | Collection of spots | 2 |  | 6
6.1 | Score | 2 |  | 6.1
7 | Sound Design | 10 |  | 7
7.1 | Sound Implimentation | 10 |  | 7.1
8 | Research Level Loader | 30 | Fernando | 8
8.1 | Level Loader created | 10 | Fernando | 8.1
9 | Menu System | 5 |  | 9
10 | Art Assets | 20 | Stephen | 10
10.1 | First Level Designed and Tested | 5 | Stephen / Fernando | 10.1
11 | Alpha Testing | 15 | All | 11
12 | Bug Fixes / Changes | 15 | All | 12
13 | Beta Testing | 15 | All | 13
14 | Final Changes | 15 | All | 14
| Total Man Hours | 190